**ADHD Task Manager**

**Iteration Plan**

**1. Key milestones**

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration starts | 24/07/2023 |
| Implement “Feel Good” Statements | 30/07/2023 |
| Develop Leaderboard Screen | 30/07/2023 |
| Develop Leaderboard Logic | 30/07/2023 |
| Develop feature to set device to do not disturb when the pomodoro timer is active | 06/08/2023 |
| Review UI for ease of use | 30/07/2023 |
| Make changes to UI based on the results of the review | 06/08/2023 |
| Test and Record Results of test for work completed | 30/07/2023 |
| Fix any bugs discovered during testing | 06/08/2023 |
| Iteration stops | 06/08/2023 |

**2. Objective’s and Completion Criteria**

**Objective 1:** Implement “Feel Good” Statements

**Criteria:** Develop logic so that “Feel Good’ Statements occur for the user once a day or when the user achieves a milestone.

**Objective 2:** Develop leaderboard screen  
 **Criteria:** Develop the leaderboard screen.

**Objective 3:** Develop the logic for the leaderboard screen  
 **Criteria:** Develop the logic for the leaderboard screen, so that users are ranked by the number of points they achieve each month.

**Objective 4:** Develop feature to set the phone to do not disturb when the pomodoro timer is active **Criteria:** The phone is set to do not disturb when the pomodoro timer is active.

**Objective 5:** Review UI for ease of use  
 **Criteria:** Review all elements of the UI to ensure that the application is easy to use, document any issues that are found, including steps to reproduce the problem.

**Objective 6:** Make changes to the UI based on the results of the review  
 **Criteria:** Fix all issues with the UI that were discovered during the review.

**Objective 7:** Test and Record Results of the test for all work completed during this iteration  
 **Criteria:** Test the work that you have done and show results on a document. Can then later combine them together.

**Objective 8:** Fix any bugs discovered during testing of the work completed  
 **Criteria:** Fix all bugs that were discovered during testing.

**3. Work Item assignments**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| Miscellaneous Work Items | | | | | | | |
| 0.1 | Pushed From C-1. Continue to work on Rewards Screen | Tidy up the Rewards Screen by adding total points and User’s Display Name on the Screen. Also add more ways to earn points in the Reward Database | NOT STARTED | Matt | 4 |  |  |
| 0.1 | Incomplete work from C1 | Reviewed Corie’s code. No issues found. | Completed | Deepak | 2 | 2 | 0 |
| Current Iteration Work Items | | | | | | | |
| 1.0 | Implement “Feel Good” Statements |  | NOT STARTED | Sam | 2 |  |  |
| 2.0 | Develop leaderboard screen |  | NOT STARTED | Matt | 1 |  |  |
| 3.0 | Develop the logic for the leaderboard screen |  | NOT STARTED | Matt | 2 |  |  |
| 4.0 | Develop feature to set the phone to do not disturb when the pomodoro timer is active |  | IN PROGRESS | Corie | 3 |  |  |
| 5.0 | Review UI for ease of use |  | NOT STARTED | Deepak | 1 |  |  |
| 6.0 | Make changes to the UI based on the results of the review |  | NOT STARTED | Deepak | 1 |  |  |
| 7.1 | Test and Record Results of test for work completed |  | NOT STARTED | Corie | 1 |  |  |
| 7.2 | Test and Record Results of test for work completed |  | NOT STARTED | Deepak | 1 |  |  |
| 7.3 | Test and Record Results of test for work completed |  | NOT STARTED | Matt | 1 |  |  |
| 7.4 | Test and Record Results of test for work completed |  | NOT STARTED | Sam | 1 |  |  |
| 8.1 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Corie | 2 |  |  |
| 8.2 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Deepak | 2 |  |  |
| 8.3 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Matt | 2 |  |  |
| 8.4 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Sam | 2 |  |  |

**5. Issues**

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
|  |  |  |

**6. Assessment**

|  |  |
| --- | --- |
| Assessment target |  |
| Assessment date |  |
| Participants | Matt, Corie, Sam, Deepak |
| Project status | Yellow |

* **Assessment against objectives**
* **Work Items: Planned compared to completed.**

* **Other concerns and deviations**