**ADHD Task Manager**

**Iteration Plan C-3**

**1. Key milestones**

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration starts | 07/08/2023 |
| Use Mobile Security Framework to analyze the app for security flaws | 20/08/2023 |
| Fix any security flaws found by the analysis | 20/08/2023 |
| Tidy Leaderboard Screen | 20/08/2023 |
| Finish developing settings | 20/08/2023 |
| Finish developing reward system | 20/08/2023 |
| Tidy Up Reward Screen | 20/08/2023 |
| Finish Profile Screen | 20/08/2023 |
| Test and Record Results of test for work completed | 20/08/2023 |
| Fix any bugs discovered during testing | 20/08/2023 |
| Iteration stops | 20/08/2023 |

**2. Objective’s and Completion Criteria**

**Objective 1:** Use Mobile Security Framework to analyze the app for security flaws

**Criteria:** Analyze the framework for security flaws. Report any flaws

**Objective 2:** Fix any security flaws found by the analysis  
 **Criteria:** Fix all security flaws found in the analysis

**Objective 3:** Tidy up leaderboard screen.  
 **Criteria:** At the moment the leaderboard screen is pretty basic. Make it look nice like the rest of the app.

**Objective 4:** Finish Settings Logic

**Criteria:** Replace the placeholder settings with our configured settings

**Objective 5:** Finish Developing the reward system  
 **Criteria:** Finish implementing the other rewards into the app

**Objective 6:** Tidy Up Reward Screen

**Criteria:** Pretty up the Reward Screen so it looks nice and professional.

**Objective 6:** Finish developing profile screen  
 **Criteria:** Finish implementing the profile screen. Now that user data is available, replace the placeholder info with user data and make the screen consistent with how the rest of the application looks.

**Objective 6:** Test and Record Results of the test for all work completed during this iteration  
 **Criteria:** Test the work that you have done and show results on a document. Can then later combine them together.

**Objective 7:** Fix any bugs discovered during testing of the work completed  
 **Criteria:** Fix all bugs that were discovered during testing.

**3. Work Item assignments**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| Miscellaneous Work Items | | | | | | | |
| 0.1 |  |  |  |  |  |  |  |
| Current Iteration Work Items | | | | | | | |
| 1.0 | Use Mobile Security Framework to analyze the app for security flaws |  | NOT STARTED | Corie | 4 |  |  |
| 2.0 | Fix any security flaws found by the analysis |  | NOT STARTED | Corie | 2 |  |  |
| 3.0 | Tidy up leaderboard screen. | Make the Leaderboard Screen Look professional | NOT STARTED | Sam | 3 |  |  |
| 4.0 | Finish Settings Logic | Replace placeholder settings with configured settings | NOT STARTED | Sam | 4 |  |  |
| 5.0 | Finish Developing the reward system | Implement System to give rewards out for logging in as well as logging in and completed task milestones | NOT STARTED | Matt | 4 |  |  |
| 5.1 | Logging in Reward | Developed logic for giving the logging in reward | NOT STARTED | Matt | 4 |  |  |
| 5.2 | Logging in Milestones | Develop logic for logging in milestones (eg logged in 3 days in a row) | NOT STARTED | Matt | 3 |  |  |
| 5.3 | Completed Task Milestones | Develop logic for completing task milestones (eg complete 10 tasks in a week) | NOT STARTED | Matt | 3 |  |  |
| 6.0 | Tidy Up Reward Screen | Make the reward Screen look professional | NOT STARTED | Deepak | 3 |  |  |
| 7.0 | Finish Profile Screen | Now that user information is available, replace placeholder data with user data. Make screen look consistent with the rest of the app | NOT STARTED | Deepak | 3 |  |  |
| 8.1 | Test and Record Results of test for work completed |  | NOT STARTED | Corie | 1 |  |  |
| 8.2 | Test and Record Results of test for work completed |  | NOT STARTED | Deepak | 1 |  |  |
| 8.3 | Test and Record Results of test for work completed |  | NOT STARTED | Matt | 1 |  |  |
| 8.4 | Test and Record Results of test for work completed |  | NOT STARTED | Sam | 1 |  |  |
| 9.1 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Corie | 2 |  |  |
| 9.2 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Deepak | 2 |  |  |
| 9.3 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Matt | 2 |  |  |
| 9.4 | Fix any bugs discovered during testing of the work completed |  | NOT STARTED | Sam | 2 |  |  |

**5. Issues**

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
|  |  |  |

**6. Assessment**

|  |  |
| --- | --- |
| Assessment target |  |
| Assessment date |  |
| Participants | Matt, Corie, Sam, Deepak |
| Project status | Yellow |

* **Assessment against objectives**
* **Work Items: Planned compared to completed.**

* **Other concerns and deviations**