ADHD Task Manager

LCAM Iteration Plan 4

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration starts | 22/05/2023 |
| Complete Revised Master Test Plan | 01/06/2023 |
| Complete Revised Risk List | 01/06/2023 |
| Complete Final Architecture document | 01/06/2023 |
| Complete Security Testing | 01/06/2023 |
| Deliver executable architecture | 01/06/2023 |
| Complete Elaboration Phase Status Assessment | 01/06/2023 |
| Iteration stops | 02/06/2023 |

# 2. Objective’s and Completion Criteria

**Objective 1:** Complete Revised Master Test Plan

**Criteria:** Completed Revised Master Test Plan, that considers the learnings from the elaboration phase iterations.

**Objective 2:** Complete Revised Risk List  
 **Criteria:** Completed Revised Risk List that considers all learnings from the elaboration phase iterations.

**Objective 3:** Complete Final Architecture document  
 **Criteria:** A completed Final Architecture document, with the final architecture design for the application.

**Objective 4:** Complete Security Testing  
 **Criteria:** Have completed security testing, with a report of any discovered vulnerabilities and suggestions of how to fix them.

**Objective 5:** Deliver executable architecture  
 **Criteria:** Have an application the is executable and includes all the architecture for the application.

**Objective 6:** Complete Elaboration Phase Status Assessment  
 **Criteria:** Completed Elaboration Phase Status Assessment

# 3. Work Item assignments

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 1.1 | Complete Revised Master Test Plan |  | Incomplete | Deepak | 1 hour |  |  |
| 2.1 | Complete Revised Risk List |  | Incomplete | Sam | 1 Hour |  |  |
| 3.1 | Complete Final Architecture document |  | Incomplete | Matt | 2 Hour |  |  |
| 4.1 | Complete Security Testing |  | Incomplete | Corie | 4 Hours |  |  |
| 5.1 | Deliver executable architecture |  | Incomplete | Sam | 1 Hour |  |  |
| 6.1 | Complete Elaboration Phase Status Assessment |  | Incomplete | Deepak | 1 Hour |  |  |