## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [8 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | ADHD Task Manager | [5 empty] | Project Name: | ADHD Task Manager
National Center: |  |  | Australia | [5 empty] | National Center: | Australia
Project Manager Name: |  |  | Team 1 | [5 empty] | Project Manager Name: | Team 1
Project Description: |  |  | Task Manager app for individuals with ADHD to complete tasks, gain rewards, and stay motivated. | [5 empty] | Project Description: | Task Manager app for individuals with ADHD to complete tasks, gain rewards, and stay motivated.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Current status description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
APP Generic risks | Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | As each use case will get implemented, group members might have different level of skills and knowledge of the coding language which can cause complications. Therefore this remains as an open risk. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
| Closed | High | Low | Closed | A group member may leave course | Due to unforseen circumstances this risk has a fair chance of occurance. | Group members to shoulder extra tasks/responsibilities | Schedule Project Resources | Tasks will need to be assgined to meet deadlines. Extra resources such as time will be required. | Team 1 gets notofied of a member leaving. | Transfer | High | Group meeting to distribute the task
| Closed | High | High | Closed | Incomplete Iteration 1.1 | Iteration 1.1 has been completed. | Hinderence to starting Iteration 1.2. | Life-cycle Costs Project Resources | Iteration 1.2 start date approaches with incomplete Iteration 1.1 | Tasks incomplete on date mentioned in the work plan | Mitigation | High | Team charter to be followed.
| Closed | High | High | Closed | Compatibility issues with different IDEs | Group members are using deffierent computer/laptopns, hence compatibility issues remains an open risk especially when working in version control | Significant impact because some members might have to redo certain components therefore taking longer than expected. | Reliability of Systems Schedule Overall project failure Technology | Members using diffeent IDEs but no issues yet, while working on the same main remote branch. | If a week before Iteration 2.1, there are issues with working on individual branches, refer to contigency plan. | Contingency | High | Find resources to address this. As a last resort, everyone uses one IDE.
| Closed | High | High | Closed | Scope creep | Scope creep continues to be a risk unless a finalised version agreed upon by the group is established. | Team members having different idea for the app. | Schedule Overall project failure Project resources Life-cycle costs Technology | As deadline approaches, core use cases either not identified or is not clear. | Not 100% sure what the core use cases are prior to end of Iteration 2.2 of LCOM | Contingency | High | Team members identify minimum agreed core use cases.
| Open | High | Medium | Red | Communication breakdown in group | Our group has consistent communication problems which needs amendment moving foreward. | Without comminucation, there is little to no awareness how things are progressing. | Schedule Overall project failure | Lack of communication especially regarding items that are central to the app's core usecases. | Meetings to be conducted on scheduled times. | Mitigation | Medium | Team charter to be followed and actioned.
| Closed | Medium | High | Closed | Depending on OS, certain files gets created which is best to be added to .gitignore. For instance, macOS and Windows may create different ones. | This is a generic risk associated when different operating systems are used. | Unnecessary files added to repo can make navigation cumbersome. | Life-cycle Costs Project resources | Unnecessary files get added which impacts navigation, and can also be the cause of generating errors. | Repoupdates from group members creates conflicts. | Contingency | Medium | A .gitignore file is created and undesired file extention gets added to it, such as .DS_Store
APP Specific Risks | Closed | High | Medium | Closed | Secure user data if external database is used. | The group has decided to use local storage. | Requires skills beyond subject studied thus far: cybersecurity | Life-cycle costs Project Resources Surety Considerations | Teachical and knowledge competency not at the required level to implement security by deadline. | A week prior to dealine, this will be dropped/ not pursued. | Avoidance | Medium | Just use local storage on device.
| Closed | High | Low | Closed | Communication Sqlite database in Android Studio | Group members have demonstrated basic competency. However, depending on use case implementations complications can arise. | Kotlin is a new language being used. It is vital for the app to comminucate with Sqlite database to add/retirieve data | Data/Information Overall project failure | Data will need to be added/retrieved from Sqlite dataabse; If core uses cases requires this but the know how is missing. | A week before deadlin, there is no evidence of logical communication with local database. | Contingency | High | Team members to look for resources and implement the logical connection between the app and the Sqlite database
| Open | High | High | Red | Usability risks | Due to failurs in testing, full usability has not been actuated and therefor cannot be closed. | Simple usability and navigation is important | Schedule Overall project failure Project resources Life-cycle costs Technology | App is difficult to navigate. | If a week before Iteration 2.1, there are issues with usability and navigation, refer to contigency plan. | Mitigation | High | Keep app as simple as possible.
| Open | High | High | Red | Functional inaccuracy | The app needs to be tested to see how it processes user input and generates outputs. This testing phase needs to pushed to next ieration in order to Close | Apps accuracy is paramount for users. | Surety Considerations data/information | Tests show inaccurate outcomes. | 2 weeks prior to deadline, if inaccuracy is not addressed refer to contigency plan. | Contingency | High | Team members to work collaborately to address functional inaccuracies.
| Open | High | Low | Yellow | Legal issues regarding user data protection | Current legal obligations will need to be referred to depending on how much of perfornal user data is collected/stored. Firebase implementation for user data is still being waited on. | Project may fail if adequate security is not implemented. Lack of cyber security knowledge. | Schedule Project resources Overall project failure | Cyber security skill set not identified as the deadline approaches. | 2 weeks prior to deadline, if not skills/resources identified, refer to contigency plan. | Contingency | Medium | Do not pursue storing data in external database.
| Open | Low | Medium | Green | Not makign the app attractive aesthetically to keep user motivated | While allowing customisation such as font colour and size will be pleasing, it can cause unpredicted complications. | A dull looking home/activity page can cause user dissatisfaction and cause demotivation. | Feasibility Project resources | Tangent or non-core usecases impacts achievement of core use cases. | Core use cases are unaccounted for. | Mitigation | Low | Drop non-core usecases such as requiring internet connection.
| Open | Low | High | Yellow | High level of customisation such as font colour and size. | If time, resource, and knowledge is available, such customisation can be considered. Colours and font will be changed for the app as the current app's beta phase is not fit for approriate visual appeal. | Such features may add additional difficulties. | Schedule | Schedule approaches deadline, and core cases are not implemented. | 3 weeks prior to deadlin, if core use cases are not implemented, then drop non-core usecases. | Acceptance | Medium | Accept core use-cases only.
| Open | High | Medium | Red | Incomplete Iterations of E3 and E4 | Incomplete work items are existent within the current phase of our assignment. These need to be implemented within next iteration. | This can and has caused delays in implementation and some branches to not be implemented. Delays and mistakes in code and in coherence with a lack of communication, has meant a non properly tested application. | Schedule Overall project failure Schedule Project Resources | Team mebers not communicating, non - updating of branch. | Tasks within E3 and E4 not bein updated or markred complete by their deadline. | Mitigation | High | E3-E4 missing items needs to be identified in team meetings.
| Open | High | High | Red | Testing Phases not being signed off and completed | Incomplete work items are existent within the current phase of our assignment. Within next iteration, all testing phases need to be achieved with integration | Because our testing phase has not been efficiently achieved, user interface and communication breakdodwn has occurred. | Schedule Overall project failure Project resources Life-cycle costs Technology | Lack of communication especially regarding items that are central to the app's core usecases. Non formulated input into the testing features and using templates for displaying data. | Upon finishing of LCAM bugs and user issues that have not yet been identified are present. | Mitigation | High | Within next iteration phase, implement full testing on a functional app.
| Closed | High | Medium | Closed | Branches being too far behind Testing in order to merge | Issues with risk early on were immediated through risk log and all branches are close tracked with testing. | The app has bugs and error which need to not only be tested but found and sought out. Not doing this properly means a non functioning user expereince. | Project Resources Time Mangement | Long commits | The merging of branch has too many changes to kotlin files and needs to be reverted. | Avoidance | High | Include a mediator and reviwer of team to facilitate implementation
| Open | High | High | Red | Overcomplication of app delaying us in testing and completion of documents | Remains open as this is a serious issue within probable cause of our app. The app's delay has come at a huge cost from technicalities that is beyond some team members capabilites. | The technicalites of the app has meant huge delays in iteration phases. Lack of knowledge has impacted on time deliverables. | Life-cycle costs Technology | Teammemebrs having difficulty completing tasks. | Non updation of iteration dealines | Mitigation | High | Eradicate design choices that are beyond teams capabilities
| Closed | Medium | Medium | Closed | Compose causing changes to the state of the app that happens outside the scope of a composable function | . Due to composables' lifecycle and properties such as unpredictable recompositions, executing recompositions of composables in different orders, or recompositions that can be discarded, composables should ideally be side-effect free. | These actions are called from a controlled environment that is aware of the lifecycle of the composable, creating a functioning file. | Surety Considerations data/information | App nagivation difficult | App crashing | Contingency | Medium | Ensured controlled environment for compositional functions.
| Closed | Medium | High | Closed | Running non-composable functions within our composable functions | Jetpack Compose side effect functions have been treated as safe spaces runniing of non-composable code is accepted. | Organises UI into a library of reusable elements. | Surety Considerations data/information | Functions fail to call | App crashing | Contingency | Medium | Ensuring composable functions calle composable functions.
| Closed | High | High | Closed | Changes to the Scope | Our mitigation strategy here is to be crystal clear with our user stories up front. Lack of communication will not be accpted upon final testing elements in order to change our scope of inclusion When an idea surfaces during development, we make a note of the idea and save it for the next phase. | Communicating and limiting our scope has ensured tangents of works have been minimsed and targeted tasks can be worked on. | Project Resources Surety Considerations | Team member communicates idelogies regarding a change or issue with outcome of application. | Multiple team members agree for a change in scope. | Avoidance | High | Ensurety of Teams vision through architecture documents, diagram and designs.
=A28:N33
LCAM CHANGES LOG:
1. | Status changed to closed for Risks from LCOM: | Risk 1,2,3,4,6,8, 12,13 | All risks that remain open have had their current status changed.
2. | Risk Additions: | Risks 12 to 20 created (table line 21) | Risk created wirth close inovlment with groups current issues
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on H6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on I6: • Risk Area: This column should be populated with the appropriate risk area.
Note on J6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on K6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on L6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on M6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on N6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources