## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | ADHD Task Manager |  |  |  |  | Project Name: | ADHD Task Manager
National Center: |  |  | Australia |  |  |  |  | National Center: | Australia
Project Manager Name: |  |  | Team 1 |  |  |  |  | Project Manager Name: | Team 1
Project Description: |  |  | Task Manager app for individual with ADHD to complete tasks, gain rewards, and stay motivated. |  |  |  |  | Project Description: | Task Manager app for individual with ADHD to complete tasks, gain rewards, and stay motivated.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
| Open | High | Low | Yellow | A group member may leave course | Group members to shoulder extra tasks/responsibilities | Schedule Project Resources | Tasks will need to be assgined to meet deadlines. Extra resources such as time will be required. | Team 1 gets notofied of a member leaving. | Transfer | High | Group meeting to distribute the task
| Closed | High | High | Closed | Incomplete Iteration 1.1 | Hinderence to starting Iteration 1.2. | Life-cycle Costs Project Resources | Iteration 1.2 start date approaches with incomplete Iteration 1.1 | Tasks incomplete on date mentioned in the work plan | Mitigation | High | Team charter to be followed.
| Open | High | Medium | Red | Secure user data if external database is used. | Requires skills beyond subject studied thus far: cybersecurity | Life-cycle costs Project Resources Surety Considerations | Teachical and knowledge competency not at the required level to implement security by deadline. | A week prior to dealine, this will be dropped/ not pursued.
| Open | Low | Medium | Green | Makign the app attractive aesthetically to keep user motivated | If core use cases are not implemented, it would be hard to stay on track. | Feasibility Project resources | Tangent or non-core usecases impacts achievement of core use cases. | Core use cases are unaccounted for. | Mitigation |  | Drop non-core usecases.
| Open | High | High | Red | Compatibility issues with different IDEs | Significant impact because some members might have to redo certain components therefore taking longer than expected. | Reliability of Systems Schedule Overall project failure Technology | Members using diffeent IDEs but no issues yet, while working on the same main remote branch. | If a week before Iteration 2.1, there are issues with working on individual branches, refer to contigency plan. | Contingency | High | Find resources to address this. As a last resort, everyone uses one IDE.
| Open | Low | High | Yellow | High level of customisation such as font colour. | Such features may add additional difficulties. | Schedule | Schedule approaches deadline, and core cases are not implemented. | 3 weeks prior to deadlin, if core use cases are not implemented, then drop non-core usecases. | Acceptance | Medium | Accept core use-cases only.
| Open | High | Low | Yellow | Communication Sqlite database in Android Studio | Kotlin is a new language being used. It is vital for the app to comminucate with Sqlite database to add/retirieve data | Data/Information Overall project failure | Data will need to be added/retrieved from Sqlite dataabse; If core uses cases requires this but the know how is missing. | A week before deadlin, there is no evidence of logical communication with local database. | Contingency | High | Team members to look for resources and implement the logical connection between the app and the Sqlite database
| Open | High | Medium | Red | Communication breakdown in group | Without comminucation, there is little to no awareness how things are progressing. | Schedule Overall project failure | Lack of communication especially items that are central to the app's core usecases. | Meetings to be conducted on scheduled times. | Mitigation | Medium | Team charter to be followed and actioned.
| Open | High | Low | Yellow | Legal issues regarding user data protection | Project may fail if adequate security is not implemented. Lack of cyber security knowledge. | Schedule Project resources Overall project failure | Cyber security skill set not identified as the deadline approaches. | 2 weeks prior to deadline, if not skills/resources identified, refer to contigency plan. | Contingency | Medium | Do not pursue storing data in external database.
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources